## Sheet1
Division Area | ID | USRN | Job Location | Stud Removal Start Date | Stud Removal Finish Date | Stud Removal Working Times | Dressing Start Date | Dressing End Date | Stud Install Start Date | Stud Install End Date | Stud Install Working times | Lining Start date | Lining End Date | Lining Working TImes | Studs TM | Lining TM | Surface Dressing TM | STB Working Times | Permit No. | time axis 2020-05-09 to 2020-09-30
South West | SD Site 45 | 36500395 | SEIFTON LANE |  |  |  | 2020-06-08 | 2020-06-10 |  |  |  | 2020-06-23 | 2020-06-25 | 07.30 - 17.00 | N/A | SCI | Some Carriageway Incursion | 07.30 - 17.00 | SD-855130
South West | SD Site10 | 36501251 | Eaton, Ticklerton, Overlay |  |  |  | 2020-06-08 | 2020-06-10 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-854650
South West | SD Site 24 | 36500840 | Balaams Jct to Broncroft Jct |  |  |  | 2020-06-10 | 2020-06-12 |  |  |  | 2020-06-23 | 2020-06-25 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854770 -1
South West | SD Site 51 | 36501184 | RUSHBURY ROAD END OF TO TOPLEY |  |  |  | 2020-06-10 | 2020-06-12 |  |  |  | 2020-06-23 | 2020-06-25 | 09.30 - 16.00 | N/A | SCI | Some Carriageway Incursion | 09.30 - 14.45 | SD-855142
South East | SD Site 38 | 4300468 | C4226 - Oakwood Road Bent Ln - Hillside Jct |  |  |  | 2020-06-11 | 2020-06-13 |  |  |  | 2020-06-24 | 2020-06-26 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855116 -1
South East | SD Site 37 | 4300800 | B4363 Junc RHS B4199 to Junc RHS B4194 | 2020-06-03 | 2020-06-06 | 20.00 - 05.00 | 2020-06-12 | 2020-06-14 | 2020-06-23 | 2020-06-25 | 09.30 - 16.00 | 2020-06-23 | 2020-06-25 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855114
South East | SD Site 6 | 4300450 | New Road, Oreton |  |  |  | 2020-06-12 | 2020-06-14 |  |  |  | 2020-06-24 | 2020-04-26 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854645
South East | SD Site 18 | 4300988 | Dog Kennel Lane - Alveley |  |  |  | 2020-06-13 | 2020-06-15 |  |  |  | 2020-06-25 | 2020-06-29 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-854745
South East | SD Site 57 | 4310247 | B4555 Knowle Sands | 2020-06-04 | 2020-06-07 | 20.00 - 05.00 | 2020-06-13 | 2020-06-17 |  |  |  | 2020-06-24 | 2020-06-26 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855467 -1
South East | SD Site 56 | 4301175 | Walton Merriwell Lane |  |  |  | 2020-06-14 | 2020-06-16 |  |  |  | 2020-06-29 | 2020-07-01 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855465
South East | SD Site 36 | 4300061 | B4375 Bethnal Lane to Jack Mytton Way | 2020-06-05 | 2020-06-08 | 20.00 - 05.00 | 2020-06-16 | 2020-06-19 | 2020-06-30 | 2020-07-02 | 09.30 - 16.00 | 2020-06-29 | 2020-07-01 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855113 -1
South West | SD Site 47 | 36500878 | BUTTS COTTAGE TO THE ROW |  |  |  | 2020-06-16 | 2020-03-18 |  |  |  | 2020-06-25 | 2020-06-30 | 07.30 - 17.00 | N/A | SCI | Some Carriageway Incursion | 07.30 - 17.00
South East | SD Site 17 | 4300863 | Cherrybrook Drive - Broseley |  |  |  | 2020-06-17 | 2020-06-19 |  |  |  | 2020-06-26 | 2020-06-30 | 07.30 - 17.00 | N/A | SCI | Some Carriageway Incursion | 07.30 - 17.00 | SD-854743 -1 -2
South West | SD Site 52 | 36501193 | SHADWELL HALL JCT-BICTON JCT |  |  |  | 2020-06-17 | 2020-03-19 |  |  |  | 2020-06-29 | 2020-07-01 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-855143
South West | SD Site 23 | 36501268 | Badger Moor |  |  |  | 2020-06-18 | 2020-06-20 |  |  |  | 2020-06-29 | 2020-07-01 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854767
South East | SD Site 16 | 4300094 | Bridge Road - Much Wenlock |  |  |  | 2020-06-19 | 2020-06-21 |  |  |  | 2020-06-30 | 2020-07-02 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854741
South East | SD Site 59 | 4310312 | B4378 Bourton | 2020-06-08 | 2020-06-11 | 20.00 - 05.00 | 2020-06-19 | 2020-06-21 | 2020-07-01 | 2020-07-03 | 09.30 - 16.00 | 2020-07-01 | 2020-07-03 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-862781 -1-3
South West | SD Site 9 | 36500849 | Black Mountain to Anchor |  |  |  | 2020-06-19 | 2020-06-21 |  |  |  | 2020-06-30 | 2020-07-02 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854649
South West | SD Site 2 | 36500601 | Cow Hall to Dowke Hill |  |  |  | 2020-06-20 | 2020-06-22 |  |  |  | 2020-06-30 | 2020-07-02 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854641 -1
South West | SD Site 3 | 36501004 | Guifron Farm Resurfacing |  |  |  | 2020-06-20 | 2020-06-22 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-854642
South West | SD Site 1 | 36500319 | Oak Meadow, Bishops Castle |  |  |  | 2020-06-21 | 2020-06-23 |  |  |  | 2020-06-28 | 2020-06-30 | 09.30 - 14.45 | N/A | Stop and Go | Some Carriageway Incursion | 09.30 - 16.00 | SD-854640 -1
South West | SD Site 7 | 36500232 | Kerry Lane, Bishops Castle |  |  |  | 2020-06-21 | 2020-06-23 |  |  |  | 2020-07-01 | 2020-07-03 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 08.00 - 17.00 | SD-854646
South West | SD Site 8 | 36500499 | Welsh St, Bishops Castle |  |  |  | 2020-06-21 | 2020-06-23 |  |  |  | 2020-07-02 | 2020-07-04 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 08.00 - 17.00 | SD-854647
Central | SD Site 19 | 34701500 | Lower Chatwell to Plaish |  |  |  | 2020-06-22 | 2020-06-24 |  |  |  | 2020-07-02 | 2020-07-04 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-854750
South West | SD Site 4 | 36500560 | Blanydree Resurfacing |  |  |  | 2020-06-22 | 2020-06-24 |  |  |  | 2020-04-02 | 2020-07-04 | 07.30 - 17.00 | N/A | Stop and Go | Some Carriageway Incursion | 07.30 - 17.00 | SD-854643
South West | SD Site 5 | 36500879 | Bwlch Resurfacing |  |  |  | 2020-06-22 | 2020-06-24 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-854644
South West | SD Site 22 | 36500645 | The Graig |  |  |  | 2020-06-23 | 2020-06-25 |  |  |  | 2020-07-02 | 2020-07-04 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854766
South West | SD Site 26 | 36500280 | B5477 Ludlow Road Church stretton |  |  |  | 2020-06-23 | 2020-06-25 |  |  |  | 2020-07-06 | 2020-07-08 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854772 -1 -2
Central | SD Site 15 | 34701625 | Shadymoor Lane |  |  |  | 2020-06-24 | 2020-06-26 |  |  |  | 2020-07-03 | 2020-07-07 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854740
South West | SD Site 21 | 36500583 | Bwlch to Purlogue |  |  |  | 2020-06-24 | 2020-06-26 |  |  |  | 2020-07-03 | 2020-07-07 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854765
South West | SD Site 20 | 36500181 | Clun to Guilden Down |  |  |  | 2020-06-25 | 2020-06-29 |  |  |  | 2020-07-03 | 2020-07-07 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-854764
South West | SD Site 43 | 36501042 | GREY BANK, Clun |  |  |  | 2020-06-25 | 2020-06-29 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-855128
South West | SD Site 49 | 36501003 | GREY BANK END OF TO GUILDEN DOWN |  |  |  | 2020-06-25 | 2020-06-29 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-855137
South West | SD Site 50 | 36501042 | HOSPITAL LN END OF-GREY BANK, Clun |  |  |  | 2020-06-25 | 2020-06-29 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-855141
South West | SD Site 55 A | 36500630 | Hope Valley | 2020-06-22 | 2020-06-25 | 20.00 - 05.00 | 2020-06-25 | 2020-06-29 | 2020-07-07 | 2020-07-09 | 09.30 - 16.00 | 2020-07-07 | 2020-07-09 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855464 -1 -2
South West | SD Site 55 B | 36500630 | Hope Valley | 2020-06-22 | 2020-06-25 | 20.00 - 05.00 | 2020-06-25 | 2020-06-29 | 2020-07-07 | 2020-07-09 | 09.30 - 16.00 | 2020-07-07 | 2020-07-09 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855464 -1 -2
South West | SD Site 48 | 36500906 | STANLEY COTTAGE ACCESS-BROCKTON FM |  |  |  | 2020-06-26 | 2020-06-30 | [5 empty] | N/A | N/A | N/A | Road Closure | 07.30 - 17.00 | SD-855135
South West | SD Site 46 | 36500841 | BECKJAY JCT B4367-BRDWARD BR JCT B4385 |  |  |  | 2020-06-29 | 2020-07-01 |  |  |  | 2020-07-13 | 2020-07-15 | 07.30 - 17.00 | N/A | Stop and Go | Road Closure | 07.30 - 17.00 | SD-855132
Central | SD Site 27 A | 34700761 | Pulley Lane |  |  |  | 2020-06-30 | 2020-07-03 |  |  |  | 2020-07-13 | 2020-07-15 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854774 -1
Central | SD Site 27 B | 34700761 | Pulley Lane |  |  |  | 2020-06-30 | 2020-07-03 |  |  |  | 2020-07-13 | 2020-07-15 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854774 -1
South West | SD Site 42 | 36500140 | DINHAM, Ludlow |  |  |  | 2020-06-30 | 2020-07-02 |  |  |  | 2020-07-13 | 2020-07-15 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855127
Central | SD Site 40 | 34701195 | WIGMORE LANE |  |  |  | 2020-07-01 | 2020-07-03 |  |  |  | 2020-07-14 | 2020-07-16 | 07.30 - 17.00 | N/A | Stop and Go | Some Carriageway Incursion | 07.30 - 17.00 | SD-855120
South West | SD Site 44 | 36500254 | LINNEY, Ludlow |  |  |  | 2020-07-01 | 2020-07-03 |  |  |  | 2020-07-15 | 2020-07-17 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855129
South West | SD Site 25 | 36500026 | Boraston Bank |  |  |  | 2020-07-02 | 2020-07-04 |  |  |  | 2020-07-13 | 2020-07-15 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854771
Central | SD Site 58 A | 34701167 | Wenlock Road, Shrewsbury |  |  |  | 2020-07-02 | 2020-07-05 |  |  |  | 2020-07-10 | 2020-07-12 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855471
Central | SD Site 58 B | 34701167 | Wenlock Road, Shrewsbury |  |  |  | 2020-07-02 | 2020-07-05 |  |  |  | 2020-07-10 | 2020-07-12 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855471
Central | SD Site 41 | 34700128 | BOW WAY, BOMERE HEATH |  |  |  | 2020-07-06 | 2020-07-08 |  |  |  | 2020-07-20 | 2020-07-22 | 07.30 - 17.00 | N/A | Some Carriageway Incursion | Some Carriageway Incursion | 07.30 - 17.00 | SD-855139
North West | SD Site 54 | 29600399 | Weston Road, Oswestry |  |  |  | 2020-07-07 | 2020-07-09 |  |  |  | 2020-07-15 | 2020-07-17 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-855460 -1
North West | SD Site 39 A | 28200793 | A528 Cockshutt to Burlton | 2020-06-23 | 2020-06-26 | 20.00 - 05.00 | 2020-07-08 | 2020-07-11 | 2020-07-20 | 2020-07-23 | 09.30 - 16.00 | 2020-07-20 | 2020-07-23 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855119 -1 -2
North West | SD Site 39 B | 28200793 | A528 Cockshutt to Burlton | 2020-06-23 | 2020-06-26 | 20.00 - 05.00 | 2020-07-08 | 2020-07-11 | 2020-07-20 | 2020-07-23 | 09.30 - 16.00 | 2020-07-20 | 2020-07-23 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855119 -1 -2
North East | SD Site 14 | 28201271 | Road to Hawkstone Park Hotel, Weston-under-Redcastle |  |  |  | 2020-07-09 | 2020-07-11 |  |  |  | 2020-07-20 | 2020-07-22 | 07.30 - 17.00 | N/A | Stop and Go | Some Carriageway Incursion | 07.30 - 17.00 | SD-854739
North East | SD Site 32 | 28200843 | B5476 - Broughton crossroads to Wem | 2020-06-30 | 2020-07-03 | 20.00 - 05.00 | 2020-07-12 | 2020-07-14 | 2020-07-24 | 2020-07-28 | 09.30 - 16.00 | 2020-07-24 | 2020-07-28 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855106 -1
North East | SD Site 33 | 28200553 | B5063 Junc with B3476 to Junc with A49 |  |  |  | 2020-07-14 | 2020-07-16 | 2020-07-29 | 2020-08-03 | 09.30 - 16.00 | 2020-07-29 | 2020-08-03 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855107 -1
North East | SD Site 12 | 28200472 | Pear Tree Lane, Whitchurch |  |  |  | 2020-07-15 | 2020-07-17 |  |  |  | 2020-07-29 | 2020-07-31 | 07.30 - 17.00 | N/A | Stop and Go | Some Carriageway Incursion | 07.30 - 17.00 | SD-854737
North East | SD Site 28 | 28210149 | A49 Hadnall to Sandy Lane | 2020-07-02 | 2020-07-05 | 20.00 - 05.00 | 2020-07-16 | 2020-07-18 | 2020-08-03 | 2020-08-05 | 09.30 - 16.00 | 2020-08-03 | 2020-08-05 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-854775-1
South East | SD Site 53 | 28200888 | A442 Espley Roundabout to Radmoor Farm Junction, Hodnet | 2020-07-01 | 2020-07-04 | 20.00 - 05.00 | 2020-07-17 | 2020-07-19 | 2020-07-31 | 2020-08-02 | 09.30 - 16.00 | 2020-07-31 | 2020-08-02 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855459
North East | SD Site 11 A | 28200999 | Shrewsbury Road, Market Drayton |  |  |  | 2020-07-20 | 2020-07-23 |  |  |  | 2020-07-27 | 2020-07-29 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854736
North East | SD Site 11 B | 28200999 | Shrewsbury Road, Market Drayton |  |  |  | 2020-07-20 | 2020-07-23 |  |  |  | 2020-07-27 | 2020-07-29 | 09.30 - 16.00 | N/A | Road Closure | Road Closure | 09.30 - 16.00 | SD-854736
North East | SD Site 31 | 28200660 | B5476 Tilstock R'bout to Tilstock 30mph sign | 2020-07-03 | 2020-07-06 | 20.00 - 05.00 | 2020-07-22 | 2020-07-24 | 2020-08-05 | 2020-08-07 | 09.30 - 16.00 | 2020-08-05 | 2020-08-07 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855104
North East | SD Site 13 | 28200585 | St Johns Street, Whitchurch |  |  |  | 2020-07-23 | 2020-07-25 |  |  |  | 2020-07-29 | 2020-07-31 | 09.30 - 16.00 | N/A | Stop and Go | Road Closure | 09.30 - 16.00 | SD-854738 -1 -2
North East | SD Site 30 A | 28200623 | A49 Hinton Bank R'bout to County Boundary | 2020-07-04 | 2020-07-07 | 20.00 - 05.00 | 2020-07-24 | 2020-07-28 | 2020-08-07 | 2020-08-11 | 09.30 - 16.00 | 2020-08-07 | 2020-08-11 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855103
North East | SD Site 30 B | 28200623 | A49 Hinton Bank R'bout to County Boundary | 2020-07-04 | 2020-07-07 | 20.00 - 05.00 | 2020-07-24 | 2020-07-28 | 2020-08-07 | 2020-08-11 | 09.30 - 16.00 | 2020-08-07 | 2020-08-11 | 09.30 - 16.00 | Road Closure | Road Closure | Road Closure | 09.30 - 16.00 | SD-855103